## Summary
Count of Task | Column Labels
Product > Cateogry > Modules | Completed | Completed / Some Changes Accrding to requirmnet | Development By MasterMind | Pending | Grand Total
Flight |  |  | 1 |  | 1
Hajj | 3 |  |  | 18 | 21
Hotel | 37 |  |  | 8 | 45
HR | 8 |  |  | 6 | 14
Sales | 9 |  |  | 11 | 20
Ticket |  |  | 13 |  | 13
Tourism |  |  |  | 13 | 13
Transport | 15 |  |  | 13 | 28
Umrah | 80 | 3 |  | 5 | 88
Visa | 11 |  |  | 15 | 26
Visitor | 1 |  |  | 11 | 12
Grand Total | 164 | 3 | 14 | 100 | 281

## Data
Sr. NO | Column1 | B2B/B2C | Segment | Task | Status
276 | Ticket | B2B/B2C | A.D.M | listing | Development By MasterMind
148 | Umrah | B2B | Activity | Activity | Completed
149 | Umrah | B2B | Activity | Allow Hotel Activity | Completed
150 | Umrah | B2B | Activity | Allow Transport Activity | Completed
151 | Umrah | B2B | Activity | Actual Hotel Activity | Completed
152 | Umrah | B2B | Activity | Actual Transport Activity | Completed
256 | Hajj | B2B/B2C | Activity Actual | Actual Hotel Activity , Actual Transport Activity | Pending
255 | Hajj | B2B/B2C | Activity Allow | Allow Hotel Activity, Allow Transport Activity | Pending
257 | Hajj | B2B/B2C | Activity Passport Management | Pending, Complete Listing | Pending
27 | HR | B2B | Attendance Report | Listing | Completed
82 | Visa | B2B | b2B Booking | Bookings | Completed
83 | Visa | B2B | b2B Booking | Pending | Completed
84 | Visa | B2B | b2B Booking | Confirm | Completed
85 | Visa | B2B | b2B Booking | All booking listings | Completed
112 | Tourism | B2B/B2C | B2B Booking | All, Pending, Confirm, Expire, Cancel | Pending
224 | Transport | B2B | b2B Booking | Bookings | Completed
225 | Transport | B2B | b2B Booking | Pending | Completed
226 | Transport | B2B | b2B Booking | Confirm | Completed
227 | Transport | B2B | b2B Booking | All booking listings | Completed
86 | Visa | B2C | b2C Booking | Bookings | Pending
87 | Visa | B2C | b2C Booking | Pending | Pending
88 | Visa | B2C | b2C Booking | Confirm | Pending
89 | Visa | B2C | b2C Booking | All | Pending
113 | Tourism | B2B/B2C | B2C Booking | All, Pending, Confirm, Expire, Cancel | Pending
228 | Transport | B2C | b2C Booking | Bookings | Pending
229 | Transport | B2C | b2C Booking | Pending | Pending
230 | Transport | B2C | b2C Booking | Confirm | Pending
231 | Transport | B2C | b2C Booking | All | Pending
96 | Visa | B2B | B2C bookings | B2C bookings | Pending
136 | Umrah | B2C | B2C Bookings | B2C Bookings | Pending
93 | Visa | B2B | B2C visa | B2C visa packags | Completed
94 | Visa | B2B | B2C visa | B2C visa Countries | Completed
269 | Ticket | B2B/B2C | Bookings | Add new Booking | Development By MasterMind
270 | Ticket | B2B/B2C | Bookings | Group Details, confirm, approved by sales, Approved by accounts, Expire, Cancel, All | Development By MasterMind
51 | Hotel | B2B | Bookings | All Bookings | Completed
52 | Hotel | B2B | Bookings | Pending Booking | Completed
53 | Hotel | B2B | Bookings | Confirm Booking | Completed
54 | Hotel | B2B | Bookings | Expire Booking | Completed
55 | Hotel | B2B | Bookings | Cancel Booking | Completed
56 | Hotel | B2B | Bookings | Approved From Sales | Completed
57 | Hotel | B2B | Bookings | Approved From Accounts | Completed
58 | Hotel | B2B | Bookings | Change Booking | Completed
59 | Hotel | B2C | Bookings | All Listing | Completed
60 | Hotel | B2C | Bookings | Pending Listing | Completed
61 | Hotel | B2C | Bookings | Confimr Listing | Completed
62 | Hotel | B2C | Bookings | Expire Listing | Completed
63 | Hotel | B2C | Bookings | Cancel Booking | Completed
159 | Umrah | B2B | BRN Management | Hotel BRN Management | Completed
160 | Umrah | B2B | BRN Management | Transport BRN Management | Completed
161 | Umrah | B2B | BRN Management | Promo Code | Completed
259 | Hajj | B2B/B2C | BRN Management | Hotel BRN | Pending
260 | Hajj | B2B/B2C | BRN Management | Transport BRN | Pending
261 | Hajj | B2B/B2C | BRN Management | Use BRN | Pending
111 | Tourism | B2B/B2C | Bulk Pligrim | All | Pending
278 | Ticket | B2B/B2C | Bulk Pligrim | add | Development By MasterMind
115 | Tourism | B2B/B2C | Change Booking | All | Pending
239 | Transport | B2B | Change Booking | Change Booking | Completed
46 | Hotel | B2B/B2C | Client | B2b Client Module | Completed
47 | Hotel | B2B/B2C | Client | B2c Client Module | Completed
48 | Hotel | B2B/B2C | Client | Externl Agent Module | Completed
49 | Hotel | B2B/B2C | Client | Sale agent module | Completed
50 | Hotel | B2B/B2C | Client | Sub agent Module | Completed
110 | Tourism | B2B/B2C | Client | All | Pending
131 | Umrah | B2B | Client | B2C | Completed
132 | Umrah | B2B | Client | B2B | Completed
133 | Umrah | B2B | Client | Sale Agent | Completed
134 | Umrah | B2B | Client | External Agent | Completed
135 | Umrah | B2B | Client | Sub Agent | Completed
219 | Transport | B2B | Client | B2C | Completed
220 | Transport | B2B | Client | B2B | Completed
221 | Transport | B2B | Client | Sale Agent | Completed
222 | Transport | B2B | Client | External Agent | Completed
223 | Transport | B2B | Client | Sub Agent | Completed
248 | Hajj | B2B | Client | B2C listing | Completed
268 | Ticket | B2B/B2C | Client | B2C, B2B, Sales Agents,all | Development By MasterMind
81 | Visa | B2B | Client | Client listing All | Completed
249 | Hajj | B2B | Client | B2B listing | Completed
250 | Hajj | B2B | Client | Sales Agent | Completed
251 | Hajj | B2B | Client External Agent | Listing | Pending
252 | Hajj | B2B | Client External Agent | Sub Agent | Pending
21 | HR | B2B | Complaints | Complaints | Pending
126 | Visitor | B2B/B2C | Confirm Visitor | Listing | Pending
119 | Visitor | B2B | Dashbaord | Page | Pending
80 | Visa | B2B | Dashboard | All Graphs | Pending
109 | Tourism | B2B | Dashboard | Page | Pending
247 | Hajj | B2B | Dashboard | Dashboard page | Pending
162 | Umrah | B2B | Data Uploader | Data Uploader Nusuk | Completed
163 | Umrah | B2B | Data Uploader | Data Uploader Nusuk ELM | Completed
164 | Umrah | B2B | Data Uploader | Data Uploader Nusuk MOFA | Completed
165 | Umrah | B2B | Data Uploader | Data Uploader Nusuk Arrival ELM | Completed
166 | Umrah | B2B | Data Uploader | Data Uploader Nusuk Departure ELM | Completed
167 | Umrah | B2B | Data Uploader | Data Uploader Nusuk City Cover Uploader | Completed
168 | Umrah | B2B | Data Uploader | Data Uploader Nusuk Visa Uploader | Completed
169 | Umrah | B2B | Data Uploader | Data Uploader Nusuk Download | Completed
170 | Umrah | B2B | Data Uploader | Data Uploader Nusuk Temp Files | Completed
258 | Hajj | B2B/B2C | Data Uploader | Same as Umrah | Pending
8 | Sales | B2B | E-Marketing | All (whatsapp, sms, email) | Pending
32 | HR | B2B | Employee Summary | Listing | Completed
24 | HR | B2B | Employees | Dashboard | Completed
25 | HR | B2B | Employees | Listing | Completed
203 | Umrah | B2B | Extra Services | Extra Services | Completed
30 | HR | B2B | Field Work | Listing | Pending
281 | Flight | B2B/B2C | Flights | All Module | Development By MasterMind
171 | Umrah | B2B | Group | Create New Group | Completed
173 | Umrah | B2B | Group | Complete Group | Completed
262 | Hajj | B2B/B2C | Group | All (Create, Manage, Delete, Pilgirm) | Pending
174 | Umrah | B2B | Group | Group Pilgrim | Completed
175 | Umrah | B2B | Group | Approved and all groups | Completed
172 | Umrah | B2B | Group Mange | Incomplete Group | Completed
176 | Umrah | B2B | Group Pilgrim | B2b Pilgrim | Completed
177 | Umrah | B2B | Group Pilgrim | b2c Pilgrim | Completed
178 | Umrah | B2B | Group Pilgrim | New Pilgrim | Completed
179 | Umrah | B2B | Group Pilgrim | Title Option | Completed
180 | Umrah | B2B | Group Pilgrim | Pilgrim Transfer | Completed
181 | Umrah | B2B | Group Pilgrim | Bulk Pilgirm And group | Completed
29 | HR | B2B | Hierarchy | Hierarchy | Completed
35 | Hotel | B2B/B2C | Hotel | Hotel List | Completed
36 | Hotel | B2B/B2C | Hotel | Hotel Countries | Completed
37 | Hotel | B2B/B2C | Hotel | Hotel Detail | Completed
38 | Hotel | B2B/B2C | Hotel | Hotel Detail Page | Completed
39 | Hotel | B2B/B2C | Hotel | Hotel Gallery | Completed
40 | Hotel | B2B/B2C | Hotel | Hotel Facilites | Completed
41 | Hotel | B2B/B2C | Hotel | Hotel Room Setup | Completed
42 | Hotel | B2B/B2C | Hotel | Hotel Amenities | Completed
43 | Hotel | B2B/B2C | Hotel | hotel Room Gallery | Completed
44 | Hotel | B2B/B2C | Hotel | Hotel room availability setup | Completed
45 | Hotel | B2B/B2C | Hotel | Hotel FAQs | Completed
64 | Hotel | B2B | Hotel | Refund Travel Check | Pending
65 | Hotel | B2B | Hotel | Change Travel Check | Pending
66 | Hotel | B2B | Hotel | Tomorrow Check In | Completed
67 | Hotel | B2B | Hotel | Tomorrow Check Out | Completed
68 | Hotel | B2B | Hotel | Pilgrim List | Completed
69 | Hotel | B2B | Hotel | Room Types | Completed
70 | Hotel | B2B | Hotel | Room Types | Completed
71 | Hotel | B2B | Hotel | Amenties | Completed
72 | Hotel | B2C | Hotel | B2c Hotel | Completed
73 | Hotel | B2C | Hotel | B2C offer | Pending
19 | Sales | B2B | Inbox | All | Pending
23 | HR | B2B | Inbox | Inbox | Pending
34 | HR | B2B | Inbox | Inbox | Pending
77 | Hotel | B2B | Inbox | Inbox | Pending
103 | Visa | B2B | Inbox | Inbox | Pending
120 | Visitor | B2B | Inbox | All | Pending
217 | Umrah | B2B | Inbox | Inbox | Pending
245 | Transport | B2B | Inbox | Inbox | Pending
9 | Sales | B2B | Initial Traning | List, Staff Remark | Pending
158 | Umrah | B2B | Invalid Entries | Manage Invalid Entries | Completed
2 | Sales | B2B | Leads | Leads sources | Pending
3 | Sales | B2B | Leads | Product | Completed
4 | Sales | B2B | Leads | Leads Management all | Completed
5 | Sales | B2B | Leads | Leads Stats (All, B2B, B2C) | Completed
26 | HR | B2B | Leaves | All, inprocess, Approved, Not Approved | Completed
31 | HR | B2B | Leaves Report | Listing | Completed
106 | Tourism | B2B | Lookups | All | Pending
204 | Umrah | B2B | Lookups | Lookups Options | Completed
271 | Ticket | B2B/B2C | New Tickets | Add | Development By MasterMind
127 | Visitor | B2B/B2C | Not Interested Visitor | Listing | Pending
125 | Visitor | B2B/B2C | Old Visitor | Listing | Pending
6 | Sales | B2B | Organic | Worksheet List | Completed
7 | Sales | B2B | Organic | Direct Platform sms, Facebook, Instagram, Linkedin, whatsapp,youtube | Completed
185 | Umrah | B2B | Package | B2B exteernal Package | Completed
186 | Umrah | B2B | Package | B2b Package | Completed
187 | Umrah | B2B | Package | B2b Package General | Completed
188 | Umrah | B2B | Package | B2b General | Pending
189 | Umrah | B2B | Package | unassign package | Completed
265 | Hajj | B2B/B2C | Package | B2B | Pending
266 | Hajj | B2B/B2C | Package | B2C | Pending
153 | Umrah | B2B | Passport Management | Pending Passport Managment | Completed
154 | Umrah | B2B | Passport Management | Completed Passport Managment | Completed
242 | Transport | B2B | Pilgrim List | Pilgrim List | Pending
100 | Visa | B2B | Pligrim List | Pligrim List | Pending
22 | HR | B2B | Query | Query | Pending
33 | HR | B2B | Query | Query | Pending
76 | Hotel | B2B | Query | Query | Pending
118 | Tourism | B2B | Query | All | Pending
130 | Visitor | B2B | Query | All | Pending
216 | Umrah | B2B | Query | Query | Pending
244 | Transport | B2B | Query | Query | Pending
102 | visa | B2B | Query | Query | Pending
114 | Tourism | B2B/B2C | Refund Booking | All | Pending
240 | Transport | B2B | Refund Booking | Refund Booking | Completed
10 | Sales | B2B | Reports | Leads product base | Completed
11 | Sales | B2B | Reports | Leads (Agent Distribution, product base lead summary, Agent base lead summary) | Pending
12 | Sales | B2B | Reports | Sales (Agent lead mature, Product lead Mature) | Completed
13 | Sales | B2B | Reports | Sales (Product lead Summary) | Pending
14 | Sales | B2B | Reports | Staff (All) | Pending
15 | Sales | B2B | Reports | Close Leads (Quality Report) | Pending
16 | Sales | B2B | Reports | Close Leads (B2B, B2C) | Completed
17 | Sales | B2B | Reports | Master Data Export (all) | Pending
263 | Hajj | B2B | Reports | Report Stat, Status Stat | Pending
264 | Hajj | B2B | Reports | Vendor | Pending
277 | Ticket | B2B/B2C | Reports | sales, Vendor | Development By MasterMind
116 | Tourism | B2B | Reports | All (Detail, Country, Category, Month, Year, Vendor) | Pending
129 | Visitor | B2B | Reports | All (Detail, Country, Category, Month, Year, Vendor) | Pending
74 | Hotel | B2B | Reports | Reports ( Detail Report , Country Wise , Hotel Wise , Vendors) | Pending
95 | Visa | B2B | Reports | All Reports (Detail, Country Wise , year Wise , Month wise ) | Pending
182 | Umrah | B2B | Reports | Report Stats | Completed / Some Changes Accrding to requirmnet
183 | Umrah | B2B | Reports | Status Stats | Completed / Some Changes Accrding to requirmnet
184 | Umrah | B2B | Reports | Vendors | Completed / Some Changes Accrding to requirmnet
235 | Transport | B2B | Reports | Reports (Details, Country , Month , Year ) | Pending
28 | HR | B2B | Roaster Report | Listing | Completed
18 | Sales | B2B | Sales Officer | staff Target | Pending
190 | Umrah | B2B | Services | Hotel | Completed
267 | Hajj | B2B/B2C | Services | All (Hotel, Transport, Visa type, Ziyaraat, extra Services, operators) | Pending
195 | Umrah | B2B | Services | Transport | Completed
196 | Umrah | B2B | Services / Transport | Transport types | Completed
197 | Umrah | B2B | Services / Transport | Transport Sectors | Completed
198 | Umrah | B2B | Services / Transport | Transport Borders | Completed
199 | Umrah | B2B | Services / Transport | Transport Comapnies | Completed
191 | Umrah | B2B | Services /hotel | Hotel Catgeories | Completed
192 | Umrah | B2B | Services /hotel | Hotel Facilites | Completed
193 | Umrah | B2B | Services /hotel | Hotel Amenties | Completed
194 | Umrah | B2B | Services /hotel | Hotel Room types | Completed
108 | Tourism | B2B | Settings | All | Pending
207 | Umrah | B2B | Settings | Website Settings | Completed
208 | Umrah | B2B | Settings | Activity log | Completed
209 | Umrah | B2B | Settings | DB backup | Completed
210 | Umrah | B2B | Settings | Agent Tpyes | Completed
211 | Umrah | B2B | Settings | Bank Accounts | Completed
212 | Umrah | B2B | Settings | Bank Categories | Completed
213 | Umrah | B2B | Settings | Umrah Calendars | Completed
214 | Umrah | B2B | Settings | Languages | Completed
215 | Umrah | B2B | Settings | Translations | Completed
128 | Visitor | B2B/B2C | Subscribers | Listing | Pending
272 | Ticket | B2B/B2C | Ticket issues | Listing | Development By MasterMind
273 | Ticket | B2B/B2C | Ticket Re issues | listing | Development By MasterMind
274 | Ticket | B2B/B2C | Ticket Refund | listing | Development By MasterMind
241 | Transport | B2B | Tomorrow Vehicle Required | Tomorrow Vehicle Required | Completed
238 | Transport | B2B | Transport Booking handling in panel | Transport Booking handling in panel | Pending
234 | Transport | B2B/B2C | Transport Data | Transport Data | Completed
237 | Transport | B2B | Transport Details | Transport Details | Pending
236 | Transport | B2B | Transport Packages | Transport Packages | Pending
232 | Transport | B2B/B2C | Transport Types | Transport Types | Completed
233 | Transport | B2B/B2C | Transport Types Categories | Transport Types Categories | Completed
137 | Umrah | B2B | Travel Check | B2B Voucher | Completed
138 | Umrah | B2B | Travel Check | All B2B Vouchers | Completed
139 | Umrah | B2B | Travel Check | Pending B2B Vouchers | Completed
140 | Umrah | B2B | Travel Check | Approved B2B Vouchers | Completed
141 | Umrah | B2B | Travel Check | Updated B2B Vouchers | Completed
142 | Umrah | B2B | Travel Check | All B2B Vouchers | Completed
143 | Umrah | B2B | Travel Check | Without Voucher Arrival | Completed
144 | Umrah | B2B | Travel Check | Cross Domain Voucher | Completed
145 | Umrah | B2B | Travel Check | Updated Cross Domain Voucher | Completed
146 | Umrah | B2C | Travel Check | B2C Voucher | Completed
147 | Umrah | B2C | Travel Check | Create B2C Voucher | Completed
253 | Hajj | B2B/B2C | Travel Check | Voucher Create | Pending
254 | Hajj | B2B/B2C | Travel Check All segment | All Vouchers | Pending
275 | Ticket | B2B/B2C | Traveling Tomorrow | listing | Development By MasterMind
124 | Visitor | B2B/B2C | Unique Visitor | Listing | Pending
1 | Sales | B2B | Users | Listing | Completed
79 | Hotel | B2B | Users | User listing | Completed
105 | Visa | B2B | Users | Users lisitng | Completed
107 | Tourism | B2B | Users | System User, Access Level | Pending
122 | Visitor | B2B | Users | Listing, Add new | Completed
205 | Umrah | B2B | Users | System User | Completed
206 | Umrah | B2B | Users | Access levels | Completed
97 | Visa | B2B | vendors | vendors | Completed
201 | Umrah | B2B | vendors | Venodrs list | Completed
279 | Ticket | B2B/B2C | Vendors | listing | Development By MasterMind
99 | Visa | B2B | visa Categories | visa Categories | Completed
90 | Visa | B2B | visa issue | visa issue | Pending
155 | Umrah | B2B | Visa Management | Manage Visa | Completed
156 | Umrah | B2B | Visa Management | Manage Mofa | Completed
157 | Umrah | B2B | Visa Management | Manage Nusuk | Completed
92 | Visa | B2B | Visa Redund | Visa Refund | Pending
91 | Visa | B2B | visa Reject | visa Reject | Pending
98 | Visa | B2B | visa Types | visa Types | Completed
202 | Umrah | B2B | Visa types | Visa types | Completed
75 | Hotel | B2B | Visitors | Visitor | Pending
117 | Tourism | B2B/B2C | Visitors | All | Pending
123 | Visitor | B2B/B2C | Visitors | Listing | Pending
243 | Transport | B2B | Visitors | Visitor | Pending
101 | visa | B2B | Visitors | Visitors | Pending
280 | Ticket | B2B/B2C | Visitors | listing | Development By MasterMind
20 | Sales | B2B | Wallet | All | Pending
78 | Hotel | B2B | Wallet | Wallet | Pending
104 | visa | B2B | Wallet | Wallet | Pending
121 | Visitor | B2B | Wallet | All | Pending
218 | Umrah | B2B | Wallet | Wallet | Pending
246 | Transport | B2B | Wallet | Wallet | Pending
200 | Umrah | B2B | Ziyarat | Ziyarat List | Completed

## Product Bookings In MIS
Sr No | Product | B2B | B2C | Offers | Panel
1 | Ticket
2 | Umrah
3 | Visa
4 | Transport
5 | Hotels
6 | Tourisum
7 | Hajj
8 | Ziarat
9 | Sale
10 | Visitor