## Summary
D-Right aPanel Status Report
Product Segments | Complete | Pending | Grand Total
ClinTa Extended | 2 | 2 | 4
ClinTa Health Care | 13 | 3 | 16
Clinta Member | 4 |  | 4
ClinTa Pharmacy | 2 |  | 2
ClinTa Web-Builder | 3 | 5 | 8
Dashboard |  | 1 | 1
Deit Facts | 5 |  | 5
Diseases | 4 |  | 4
Documentations | 7 |  | 7
Health Care | 36 | 2 | 38
Investigation |  | 10 | 10
LookUps | 8 |  | 8
Main | 3 | 9 | 12
Medicine | 5 | 2 | 7
Support Tickets |  | 2 | 2
System | 4 |  | 4
Laboratories | 1 | 1 | 2
Grand Total | 97 | 37 | 134

## Data
Sr. NO | Product | Segment | Sub Segment | Task | Status
1 | Clinta Member | List | Listing |  | Complete
2 | Clinta Member | List | Filters |  | Complete
3 | Clinta Member | List | Shift to Preimum |  | Complete
5 | Clinta Member | List | View |  | Complete
7 | Dashboard | Graphs |  |  | Pending
8 | Diseases | Diseases | Listing |  | Complete
9 | Diseases | Diseases | Add |  | Complete
10 | Diseases | Diseases | Delete |  | Complete
11 | Diseases | Diseases | Update |  | Complete
12 | Documentations | FAQS | Crud |  | Complete
13 | Health Care | Diet Plan | Crud |  | Complete
14 | Health Care | Dry Fruit and Seeds | CRUD |  | Complete
15 | Health Care | Exercise | Listing |  | Complete
16 | Health Care | Exercise | Add |  | Complete
17 | Health Care | Exercise | Delete |  | Complete
18 | Health Care | Exercise | Update |  | Complete
19 | Health Care | Fruit | Listing |  | Complete
20 | Health Care | Fruit | Add |  | Complete
21 | Health Care | Fruit | Delete |  | Complete
22 | Health Care | Fruit | Update |  | Complete
23 | Health Care | Fruit | Details and Update |  | Complete
24 | Health Care | Miscellaneous | Add |  | Complete
25 | Health Care | Miscellaneous | Update |  | Complete
26 | Health Care | Miscellaneous | Delete |  | Complete
27 | Health Care | Miscellaneous | Listing |  | Complete
28 | Health Care | Miscellaneous | Details and Update |  | Complete
29 | Health Care | Pulses-Grains | Add |  | Complete
30 | Health Care | Pulses-Grains | Update |  | Complete
31 | Health Care | Pulses-Grains | Delete |  | Complete
32 | Health Care | Pulses-Grains | Listing |  | Complete
33 | Health Care | Pulses-Grains | Details and Update |  | Complete
34 | Health Care | Stats | Premium Members |  | Pending
35 | Health Care | Stats | Basic Members |  | Pending
36 | Health Care | Tips and Guides | Add |  | Complete
37 | Health Care | Tips and Guides | Update |  | Complete
38 | Health Care | Tips and Guides | Delete |  | Complete
39 | Health Care | Tips and Guides | Listing |  | Complete
40 | Health Care | Vegetable | Add |  | Complete
41 | Health Care | Vegetable | Update |  | Complete
42 | Health Care | Vegetable | Delete |  | Complete
43 | Health Care | Vegetable | Listing |  | Complete
44 | Health Care | Vegetable | Details and Update |  | Complete
45 | Health Care | Dry Fruits | Add |  | Complete
46 | Health Care | Dry Fruits | Update |  | Complete
47 | Health Care | Dry Fruits | Delete |  | Complete
48 | Health Care | Dry Fruits | Listing |  | Complete
49 | Health Care | Dry Fruits | Details and Update |  | Complete
50 | Health Care | Work out Plan | Crud |  | Complete
51 | Investigation | Lab Reports | Crud |  | Pending
52 | Investigation | Lab Reports | Filters |  | Pending
53 | Investigation | Radiology | Crud |  | Pending
54 | Investigation | Radiology | Filters |  | Pending
55 | Main | Admin Activity | Crud |  | Pending
56 | Main | Admin Activity | Filters |  | Pending
57 | Main | Customer | Listing |  | Pending
58 | Main | Customer | Add |  | Pending
59 | Main | Customer | Update |  | Pending
60 | Main | Customer | Delete |  | Pending
61 | Main | Customer | Filters |  | Pending
62 | Laboratories | Laboratories | Crud |  | Complete
63 | Laboratories | Laboratories | Filters |  | Complete
64 | Main | Login | Login |  | Complete
65 | Main | Login | Forget Password |  | Pending
66 | Main | Specialities | CRUD |  | Complete
67 | Main | Specialities | Filters |  | Complete
72 | Medicine | Company | Crud |  | Complete
73 | Medicine | Company | Filter |  | Complete
74 | Medicine | Forms | Crud |  | Complete
75 | Medicine | List | Crud |  | Complete
76 | Medicine | List | Filter |  | Complete
77 | Medicine | Take Type | Crud |  | Complete
78 | Medicine | Timing | Crud |  | Complete
79 | LookUps | LookUps (Nav) | Listing |  | Complete
80 | LookUps | LookUps (Nav) | Add |  | Complete
81 | LookUps | LookUps (Nav) | Update |  | Complete
82 | LookUps | LookUps (Nav) | Delete |  | Complete
83 | LookUps | LookUps (Nav) | Filters |  | Complete
84 | Main | Admin Approval | List |  | Pending
85 | Documentations | FAQS | Crud |  | Complete
86 | Documentations | Diet Plan | Crud |  | Complete
87 | Documentations | Work out Plan | Crud |  | Complete
88 | Documentations | Tips and Guides | Crud |  | Complete
89 | Documentations | Tips and Guides | Filter |  | Complete
90 | Documentations | Exercise | Crud |  | Complete
91 | Support Tickets | ClinTa Extended | Filter |  | Pending
92 | Support Tickets | ClinTa Extended | Crud |  | Pending
93 | Deit Facts | Fruits | Crud |  | Complete
94 | Deit Facts | Vegetable | Crud |  | Complete
95 | Deit Facts | Pulses-Grains | Crud |  | Complete
96 | Deit Facts | Dry Fruits | Crud |  | Complete
97 | Deit Facts | Miscellaneous | Crud |  | Complete
98 | System | Users | Add |  | Complete
100 | LookUps | List | Filter |  | Complete
101 | LookUps | LookUps Options | Crud |  | Complete
102 | LookUps | LookUps Options | Filter |  | Complete
103 | Investigation | Lab Reports | Crud |  | Pending
104 | Investigation | Radiology | Crud |  | Pending
105 | Investigation | Lab Reports | Filter |  | Pending
106 | Investigation | Radiology | Filter |  | Pending
107 | Investigation | Lab Reports Parameters | Crud |  | Pending
108 | Investigation | Radiology Parameters | Crud |  | Pending
109 | ClinTa Web-Builder | Sponsors | Crud | Image Not Submiit | Complete
| ClinTa Web-Builder | Sponsors Product | Crud | Image Not Submiit | Complete
111 | ClinTa Web-Builder | Doctor Websites | Crud | Image Not Submiit | Pending
112 | ClinTa Web-Builder | Doctor Websites | Filter |  | Pending
113 | ClinTa Web-Builder | Hospital Websites | Crud | except Images save | Complete
114 | ClinTa Web-Builder | Hospital Websites | Filter |  | Complete
115 | ClinTa Web-Builder | Image Database | Crud |  | Complete
116 | ClinTa Web-Builder | General Banners | Crud |  | Complete
117 | ClinTa Health Care | Branches | Crud |  | Pending
118 | ClinTa Health Care | RCCS | Add |  | Complete
119 | ClinTa Health Care | RCCS | Update |  | Complete
120 | ClinTa Health Care | RCCS | Delete |  | Complete
121 | ClinTa Health Care | RCCS | List |  | Complete
121 | ClinTa Health Care | RCCS | ADD Recipt |  | Complete
122 | ClinTa Health Care | RCCS | Filter |  | Complete
123 | ClinTa Health Care | Discount Center | Crud |  | Pending
124 | ClinTa Health Care | Support Vidoes | Add |  | Complete
125 | ClinTa Health Care | Support Vidoes | Update |  | Complete
126 | ClinTa Health Care | Support Vidoes | Delete |  | Complete
127 | ClinTa Health Care | Support Vidoes | List |  | Complete
128 | ClinTa Health Care | Diet Categories | Add |  | Complete
129 | ClinTa Extended | Database Compare | Update |  | Pending
130 | ClinTa Extended | Profile | Delete |  | Pending
131 | ClinTa Extended | Deafut Configration | List |  | Complete
132 | ClinTa Extended | Deafut Lookup | Crud |  | Complete
133 | ClinTa Pharmacy | Pharmacy Profile | Crud |  | Complete
134 | ClinTa Pharmacy | Pharmacy Profile | Filter |  | Complete
135 | System | Users | Update |  | Complete
136 | System | Users | Delete |  | Complete
137 | System | Users | Listing |  | Complete
138 | ClinTa Health Care | Diet Categories | Update |  | Complete
139 | ClinTa Health Care | Diet Categories | Delete |  | Complete
140 | ClinTa Health Care | Diet Categories | List |  | Complete
Clinta