## Summary
D-Right aPanel Status Report
Products | Pending | Complete | Grand Total
Main | 20 | 2 | 22
Dashboard | 1 |  | 1
Diseases | 4 |  | 4
Documentations | 1 |  | 1
Investigation | 4 |  | 4
Medicine | 5 |  | 5
Clinta Member | 6 |  | 6
Health Care | 13 | 26 | 39
Grand Total | 54 | 28 | 82

## Data
Sr. NO | Product | Segment | Sub Segment | Task | Status
1 | Clinta Member | List | Lsiting |  | Pending
2 | Clinta Member | List | Filters |  | Pending
3 | Clinta Member | List | Lisiting |  | Pending
4 | Clinta Member | List | Add |  | Pending
5 | Clinta Member | List | Delete |  | Pending
6 | Clinta Member | List | Update |  | Pending
7 | Dashboard | Graphs |  |  | Pending
8 | Diseases | Diseases | Lisiting |  | Pending
9 | Diseases | Diseases | Add |  | Pending
10 | Diseases | Diseases | Delete |  | Pending
11 | Diseases | Diseases | Update |  | Pending
12 | Documentations | FAQS | Crud |  | Pending
13 | Health Care | Diet Plan | Crud |  | Pending
14 | Health Care | Dry Fruit and Seeds | CRUD |  | Pending
15 | Health Care | Exercise | Lisiting |  | Pending
16 | Health Care | Exercise | Add |  | Pending
17 | Health Care | Exercise | Delete |  | Pending
18 | Health Care | Exercise | Update |  | Pending
19 | Health Care | Fruit | Lisiting |  | Complete
20 | Health Care | Fruit | Add |  | Complete
21 | Health Care | Fruit | Delete |  | Complete
22 | Health Care | Fruit | Update |  | Complete
23 | Health Care | Fruit | Details and Update |  | Complete
24 | Health Care | Miscellaneous | Add |  | Complete
25 | Health Care | Miscellaneous | Update |  | Complete
26 | Health Care | Miscellaneous | Delete |  | Complete
27 | Health Care | Miscellaneous | Lisitng |  | Complete
28 | Health Care | Miscellaneous | Details and Update |  | Complete
29 | Health Care | Pulses-Grains | Add |  | Complete
30 | Health Care | Pulses-Grains | Update |  | Complete
31 | Health Care | Pulses-Grains | Delete |  | Complete
32 | Health Care | Pulses-Grains | Lisitng |  | Complete
33 | Health Care | Pulses-Grains | Details and Update |  | Complete
34 | Health Care | Stats | Premium Members |  | Pending
35 | Health Care | Stats | Basic Members |  | Pending
36 | Health Care | Tips and Guides | Add |  | Pending
37 | Health Care | Tips and Guides | Update |  | Pending
38 | Health Care | Tips and Guides | Delete |  | Pending
39 | Health Care | Tips and Guides | Lisitng |  | Pending
40 | Health Care | Vegetable | Add |  | Complete
| Health Care | All | Nutrtiton Detail |  | Complete
41 | Health Care | Vegetable | Update |  | Complete
42 | Health Care | Vegetable | Delete |  | Complete
43 | Health Care | Vegetable | Lisitng |  | Complete
44 | Health Care | Vegetable | Details and Update |  | Complete
45 | Health Care | Dry Fruits | Add |  | Complete
46 | Health Care | Dry Fruits | Update |  | Complete
47 | Health Care | Dry Fruits | Delete |  | Complete
48 | Health Care | Dry Fruits | Lisitng |  | Complete
49 | Health Care | Dry Fruits | Details and Update |  | Complete
50 | Health Care | Work out Plan | Crud |  | Pending
51 | Investigation | Lab Reports | Crud |  | Pending
52 | Investigation | Lab Reports | Filters |  | Pending
53 | Investigation | Radiology | Crud |  | Pending
54 | Investigation | Radiology | Filters |  | Pending
55 | Main | Admin Activity | List |  | Pending
56 | Main | Admin Activity | Filters |  | Pending
57 | Main | Customer | Lisitng |  | Pending
58 | Main | Customer | Add |  | Pending
59 | Main | Customer | Update |  | Pending
60 | Main | Customer | Delete |  | Pending
61 | Main | Customer | Filters |  | Pending
62 | Main | Laboratories | Crud |  | Pending
63 | Main | Laboratories | Filters |  | Pending
64 | Main | Login | Login |  | Pending
65 | Main | Login | Forget Password |  | Pending
66 | Main | Specialities | CRUD |  | Pending
67 | Main | Specialities | Filters |  | Pending
68 | Main | System Users | List |  | Complete
69 | Main | System Users | Filter |  | Pending
70 | Main | System Users | Access Level |  | Pending
71 | Main | System Users | CRUD |  | Complete
72 | Medicine | Company | Crud |  | Pending
73 | Medicine | Forms | Crud |  | Pending
74 | Medicine | List | Crud |  | Pending
75 | Medicine | Take Type | Crud |  | Pending
76 | Medicine | Timing | Crud |  | Pending
77 | Main | LookUps | Lisiting |  | Pending
78 | Main | LookUps | Add |  | Pending
79 | Main | LookUps | Update |  | Pending
80 | Main | LookUps | Delete |  | Pending
81 | Main | LookUps | Filters |  | Pending
82 |  |  |  |  | Pending
83
84