## Summary
D-Right aPanel Status Report
Product Segments | Complete | Pending | Grand Total
ClinTa Extended | 3 | 3 | 6
ClinTa Health Care | 15 | 3 | 18
Clinta Member | 4 |  | 4
ClinTa Pharmacy | 2 |  | 2
ClinTa Web-Builder | 8 |  | 8
Dashboard |  | 1 | 1
Deit Facts | 5 |  | 5
Diseases | 4 |  | 4
Documentations | 7 |  | 7
Health Care | 36 |  | 36
Investigation | 10 |  | 10
LookUps | 8 |  | 8
Main | 9 | 2 | 11
Medicine | 7 |  | 7
Support Tickets | 2 |  | 2
System | 4 |  | 4
Laboratories | 2 |  | 2
Grand Total | 126 | 9 | 135

## Data
Sr. NO | Product | Segment | Sub Segment | Task | Status | Comments | Developer Comment
1 | Clinta Member | List | Listing |  | Complete | All Names not shown?? | Maybe Fault in ur Data entry
2 | Clinta Member | List | Filters |  | Complete | Only one filter, to search member using name | Completed
3 | Clinta Member | List | Shift to Preimum |  | Complete | How is that working?
4 | Clinta Member | List | View |  | Complete | Undefined, the link takes you somwhere else
5 | Dashboard | Graphs |  |  | Pending
6 | Diseases | Diseases | Listing |  | Complete | Name must be reqiured before entering category | Done
7 | Diseases | Diseases | Add |  | Complete | Working
8 | Diseases | Diseases | Delete |  | Complete | Working
9 | Diseases | Diseases | Update |  | Complete | Working
10 | Documentations | FAQS | Crud |  | Complete | Issue in Update , Purpose of these FAQs? | Its in Clinta Apanel
11 | Health Care | Diet Plan | Crud |  | Complete | Where on patient portal? Unnecessary last row | Its on Documentation Segment Kindly Check Properly
12 | Health Care | Dry Fruit and Seeds | CRUD |  | Complete | Same as point 41-43 except for Read
13 | Health Care | Exercise | Listing |  | Complete | No available data!!! | Becoz no Data entry in Database
14 | Health Care | Exercise | Add |  | Complete | Working
15 | Health Care | Exercise | Delete |  | Complete | Working
16 | Health Care | Exercise | Update |  | Complete | Not working correctly, remove extra line space when "Enter" clicked | Could you please clarify what’s not working
17 | Health Care | Fruit | Listing |  | Complete | Working
18 | Health Care | Fruit | Add |  | Complete | Can't add nutritional items. Not added on patient portal!! | Could you please clarify
19 | Health Care | Fruit | Delete |  | Complete | Working
20 | Health Care | Fruit | Update |  | Complete | Working
21 | Health Care | Fruit | Details and Update |  | Complete | Working
22 | Health Care | Miscellaneous | Add |  | Complete | Can't add nutritional items. Not added on patient portal!! | Could you please clarify
23 | Health Care | Miscellaneous | Update |  | Complete | Working
24 | Health Care | Miscellaneous | Delete |  | Complete | Working
25 | Health Care | Miscellaneous | Listing |  | Complete | Working
26 | Health Care | Miscellaneous | Details and Update |  | Complete | Working
27 | Health Care | Pulses-Grains | Add |  | Complete | Not added on Patient Portal | Already Explained
28 | Health Care | Pulses-Grains | Update |  | Complete | Working
29 | Health Care | Pulses-Grains | Delete |  | Complete | Working
30 | Health Care | Pulses-Grains | Listing |  | Complete | Working
31 | Health Care | Pulses-Grains | Details and Update |  | Complete | Working
32 | Health Care | Tips and Guides | Add |  | Complete | Working
33 | Health Care | Tips and Guides | Update |  | Complete | Not working correctly, remove extra line space when "Enter" clicked
34 | Health Care | Tips and Guides | Delete |  | Complete | Working
35 | Health Care | Tips and Guides | Listing |  | Complete | Working
36 | Health Care | Vegetable | Add |  | Complete | Not added on Patient Portal | Already Explained
37 | Health Care | Vegetable | Update |  | Complete | Working
38 | Health Care | Vegetable | Delete |  | Complete | Working
39 | Health Care | Vegetable | Listing |  | Complete | Working
40 | Health Care | Vegetable | Details and Update |  | Complete | Working
41 | Health Care | Dry Fruits | Add |  | Complete | Not added on Patient Portal | Already Explained
42 | Health Care | Dry Fruits | Update |  | Complete | Working
43 | Health Care | Dry Fruits | Delete |  | Complete | Working
44 | Health Care | Dry Fruits | Listing |  | Complete | Working
45 | Health Care | Dry Fruits | Details and Update |  | Complete | Error 404 | Done
46 | Health Care | Work out Plan | Crud |  | Complete | Where on patient portal? Update not working correctly | In Doucmentation segments
47 | Investigation | Lab Reports | Crud |  | Complete | Name must be required before entering category and type. | Completed
48 | Investigation | Lab Reports | Filters |  | Complete | Filter required based on category and type as well | Completed
49 | Investigation | Radiology | Crud |  | Complete | Name must be required before entering category and type. | Completed
50 | Investigation | Radiology | Filters |  | Complete | Working
51 | Main | Admin Activity | Lisiting |  | Complete | No crud required and present in Admin Activity!!? | no Crud
52 | Main | Admin Activity | Filters |  | Complete | Working
53 | Main | Customer | Listing |  | Complete
54 | Main | Customer | Add |  | Complete
55 | Main | Customer | Update |  | Complete
56 | Main | Customer | Delete |  | Complete
58 | Laboratories | Laboratories | Crud |  | Complete | No webite link in update? Sub-Domain Creation? Expiry? | Kindly Check this segment in Clinta Apanel
59 | Laboratories | Laboratories | Filters |  | Complete | Working
60 | Main | Login | Login |  | Complete | Where in A-Panel?? | Main Login Page…
61 | Main | Specialities | CRUD |  | Complete | Main/Head Row should have relevant names with the content. What is total images column about?? Usage of add heading?? | done
62 | Main | Specialities | Filters |  | Complete | Working |  | 0
63 | Medicine | Company | Crud |  | Complete | Check new Medicine??? Add not working. Sort Number?? Data without company name?? Data deletion not working | Done apenl link (https://www.clinta.biz/apanel/module/company/list)
64 | Medicine | Company | Filter |  | Complete | Working
65 | Medicine | Forms | Crud |  | Complete | Sort Order should start from 1 to avoid confusion | already sorted
66 | Medicine | List | Crud |  | Complete | Show Medicine Name in the Table!! | Done
67 | Medicine | List | Filter |  | Complete | Not working based on medicine name! | Done
68 | Medicine | Take Type | Crud |  | Complete | Working
69 | Medicine | Timing | Crud |  | Complete | Sort Order issue
70 | LookUps | LookUps (Nav) | Listing |  | Complete | Working
71 | LookUps | LookUps (Nav) | Add |  | Complete | Working
72 | LookUps | LookUps (Nav) | Update |  | Complete | How to add additional info? Like in blood groups... | https://www.clinta.biz/apanel/module/extended_default_lookups/list
73 | LookUps | LookUps (Nav) | Delete |  | Complete | Working
74 | LookUps | LookUps (Nav) | Filters |  | Complete | Working
75 | Main | Admin Approval | List |  | Complete | Working
76 | Documentations | FAQS | Crud |  | Complete | Same as point 10 except for Read
77 | Documentations | Diet Plan | Crud |  | Complete | Same as point 11 except for Read
78 | Documentations | Work out Plan | Crud |  | Complete | Same as point 46 except for Read
79 | Documentations | Tips and Guides | Crud |  | Complete | Same as point 32-34 except for Read
80 | Documentations | Tips and Guides | Filter |  | Complete | No filter present!! | Not in Clinta apenl
81 | Documentations | Exercise | Crud |  | Complete | Same as points 14-16 except for Read
82 | Support Tickets | ClinTa Extended | Filter |  | Complete
83 | Support Tickets | ClinTa Extended | Crud |  | Complete
84 | Deit Facts | Fruits | Crud |  | Complete | Same as points 18-20 except for Read
85 | Deit Facts | Vegetable | Crud |  | Complete | Same as points 36-38 except for Read
86 | Deit Facts | Pulses-Grains | Crud |  | Complete | Same as points 27-30 except for Read
87 | Deit Facts | Dry Fruits | Crud |  | Complete | Same as points 41-43, 12
88 | Deit Facts | Miscellaneous | Crud |  | Complete | Same as points 22-24 except for Read
89 | System | Users | Add |  | Complete | Error! Undefined | Fixed
90 | LookUps | List | Filter |  | Complete
91 | LookUps | LookUps Options | Crud |  | Complete | Same as points 71-73, except for read
92 | LookUps | LookUps Options | Filter |  | Complete | Same as point 74
93 | Investigation | Lab Reports | Crud |  | Complete | Same as point 47
94 | Investigation | Radiology | Crud |  | Complete | Same as point 49
95 | Investigation | Lab Reports | Filter |  | Complete | Same as point 48
96 | Investigation | Radiology | Filter |  | Complete | Same as point 50
97 | Investigation | Lab Reports Parameters | Crud |  | Complete | Working but No Data Available !! | no Data enter
98 | Investigation | Radiology Parameters | Crud |  | Complete | Working
99 | ClinTa Web-Builder | Sponsors | Crud |  | Complete | Image not shown even after submitting | Fixed
100 | ClinTa Web-Builder | Sponsors Product | Crud |  | Complete | Image not shown even after submitting | Fixed
101 | ClinTa Web-Builder | Doctor Websites | Crud |  | Complete
102 | ClinTa Web-Builder | Doctor Websites | Filter |  | Complete
103 | ClinTa Web-Builder | Hospital Websites | Crud |  | Complete | Takes loading time, edit not working
104 | ClinTa Web-Builder | Hospital Websites | Filter |  | Complete | Not working, Ajax Error
105 | ClinTa Web-Builder | Image Database | Crud |  | Complete | Working
106 | ClinTa Web-Builder | General Banners | Crud |  | Complete | Solution?
107 | ClinTa Health Care | Branches | Crud |  | Complete
108 | ClinTa Health Care | RCCS | Add |  | Complete | Working, add asterisk to show mandatory fields | Done
109 | ClinTa Health Care | RCCS | Update |  | Complete | Not working correctly | Done
110 | ClinTa Health Care | RCCS | Delete |  | Complete | Working
111 | ClinTa Health Care | RCCS | List |  | Complete | Working
112 | ClinTa Health Care | RCCS | ADD Recipt |  | Complete | Total Receipts 0 even after adding! | Done
113 | ClinTa Health Care | RCCS | Filter |  | Complete | Takes a lot of time
114 | ClinTa Health Care | Discount Center | Crud |  | Pending
115 | ClinTa Health Care | Discounts Center List Discounts Center Doctors | Crud |  | Pending
116 | ClinTa Health Care | Discount Center Offer | Crud |  | Pending
117 | ClinTa Health Care | Support Vidoes | Add |  | Complete | Working
118 | ClinTa Health Care | Support Vidoes | Update |  | Complete | Working
119 | ClinTa Health Care | Support Vidoes | Delete |  | Complete | Working
120 | ClinTa Health Care | Support Vidoes | List |  | Complete | No data available
121 | ClinTa Health Care | Diet Categories | Add |  | Complete | Working
122 | ClinTa Extended | Database Compare | List |  | Pending
123 | ClinTa Extended | Profile | Crud |  | Complete
124 | ClinTa Extended | Deafut Configration | List |  | Complete | Working
125 | ClinTa Extended | Deafut Lookup | Crud |  | Complete | Working
126 | ClinTa Pharmacy | Pharmacy Profile | Crud |  | Complete | MAC Address and Expiry Date not shown in Details after adding new data | Fixed
127 | ClinTa Pharmacy | Pharmacy Profile | Filter |  | Complete | Working
128 | System | Users | Update |  | Complete | Working
129 | System | Users | Delete |  | Complete | Working
130 | System | Users | Listing |  | Complete | Working
131 | ClinTa Health Care | Diet Categories | Update |  | Complete | Working
132 | ClinTa Health Care | Diet Categories | Delete |  | Complete | Working
133 | ClinTa Health Care | Diet Categories | List |  | Complete | Working
134 | ClinTa Extended | Profile Detail | Crud |  | Complete
135 | ClinTa Extended | Add user | Crud |  | Complete
136 | Main | Specialities-Gallery | Crud |  | Complete